## Low_Moderate_High_WBS
Task # | Task | Responsibility | Start Date | End Date | Notes / Questions
1 | Design/Build System |  |  |  | System should already be operational; CSP should list any gaps and identify dates for remediation to meet federal mandates and FedRAMP requirements
1.1 | Remediate Gaps (CSP should insert any identified gaps and timelines associated with remediation below) | CSP
1.2 | <Gap 1> | CSP |  |  | CSP insert gaps here; add lines if needed.
1.3 | <Gap 2> | CSP
2 | Develop and Finalize SSP |  |  |  | Task 2.9 should be date of completed SSP. This section does not necessarily need to be linear as multiple tasks can be worked durring the same time period.
2.1 | Provide completed IPR, WBS to FedRAMP PMO | Agency, CSP
2.2 | SSP Finalized and delivered to Agency | CSP
2.3 | Agency reviewed draft SSP | Agency
2.4 | Schedule Kick-off meeting | PMO, Agency, CSP
2.5 | Prepare Kick-off presentation and hold Kickoff Meeting | CSP, Agency, PMO |  |  | *Draft deck must be provided to the FedRAMP PMO in advance of scheduling the Kick Off Meeting to allow time for PMO feedback.
2.6 | CSP remediates draft SSP | CSP
2.7 | Agency validates CSP remediation | Agency
2.8 | Agency documents awareness of Customer Responsibilities | Agency
2.9 | Agency approves SSP | Agency
3 | Develop and Finalize SAP |  |  |  | Task 3.5 should be date of finalized and approved SAP.
3.1 | 3PAO/CSP SAP Finalized - Delivered to Agency | CSP, 3PAO
3.2 | Agency Reviewed and Commented on SAP | Agency
3.3 | CSP/3PAO Remediated Draft SAP Comments | CSP, 3PAO
3.4 | Agency Validated Comments | Agency
3.5 | Agency Approved SAP | Agency
4 | Develop and Finalize SAR / POA&M
4.1 | Begin 3PAO Security Assessment | 3PAO |  |  | *Start date should be within 6 months of In Process designation date
4.2 | 3PAO issues SAR to CSP | 3PAO
4.3 | Remediate Risks | CSP
4.4 | Delivery of final SAR | 3PAO
4.5 | Develop and deliver POA&M | CSP
4.6 | Hold SAR Debrief | CSP, 3PAO, Agency, PMO |  |  | Formal meeting with FedRAMP PMO, Agency, 3PAO, and CSP
4.7 | Review & Approve SAR | Agency
5 | Final Agency Review and ATO |  |  |  | *Agency can add additional tasks into this section if there are additional agency specific tasks not identified.
5.1 | Agency final review | Agency
5.2 | Agency submits CSO’s authorization package to the Agency AO for final approval and issuance of the ATO | Agency
5.3 | Agency issues ATO and provides copy to FedRAMP via info@fedramp.gov | Agency
6 | FedRAMP PMO Review and FedRAMP Authorized Decision
6.1 | The CSP and 3PAO upload all required security package material to OMB MAX | CSP, 3PAO
6.2 | The FedRAMP PMO reviews the package and releases an Agency Package Review Report | PMO |  |  | Please leave this section blank as the PMO will fill out. The FedRAMP PMO is committed to a package reiew within 10 days; CSP package is put in queue according to order received.
6.3 | Conduct review meeting with agency, CSP, and 3PAO to discuss questions on outstanding items reflected in the Agency Package Review Report | CSP, 3PAO, Agency, PMO |  |  | Once a complete security package along with the intial agency ATO are uploaded to Max.gov the PMO will notify the CSP as to the PMO's current queue status.
6.4 | Remediation of PMO findings and delivery of updates to PMO | CSP, 3PAO |  |  | The timeline to Authorization will vary depending on the quality of the security package submitted to the PMO along with number of packages that are currently in review with the PMO.
6.5 | PMO informs CSP that FedRAMP Authorization designation has been achieved | PMO
6.6 | Marketplace listing for CSO is updated to reflect FedRAMP Authorized and date of authorization | PMO |  |  | *End date should be within 1 year of In Process designation date