## LowModerateHigh WBS
Task # | Task | Responsibility | Start Date | End Date | Notes / Questions
1 | Design/Build System |  |  |  | System should already be operational; CSP should list any gaps and identify dates for remediation to meet federal mandates and FedRAMP requirements
1.1 | Remediate Gaps (CSP should insert any identified gaps and timelines associated with remediation below) | CSP
1.1.1 | <Gap 1> | CSP |  |  | CSP insert gaps here; add lines if needed
1.1.2 | <Gap 2> | CSP
2 | Develop and Finalize SSP |  |  |  | End date should be date of finalized SSP
2.1 | Provide completed WBS to FedRAMP PMO | CSP, Agency
2.2 | SSP Finalized and delivered to Agency | CSP
2.3 | Agency reviewed draft SSP | Agency
2.4 | Schedule Kick-off meeting | PMO, Agency, CSP
2.5 | Prepare Kick-off presentation and hold Kickoff Meeting | CSP, Agency, PMO |  |  | *Provide draft to the FedRAMP PMO for review and feedback at least 7 days before kickoff meeting
2.6 | CSP remediates draft SSP | CSP
2.7 | Agency validates CSP remediation | Agency
2.8 | Agency documents awareness of Customer Responsibilities | Agency
2.9 | Agency approves SSP | Agency
3 | Develop and Finalize SAP |  |  |  | End date should be date of finalized SAP
3.1 | 3PAO/CSP SAP Finalized - Delivered to Agency | CSP, 3PAO
3.2 | Agency Reviewed and Commented on SAP | Agency
3.3 | CSP/3PAO Remediated Draft SAP Comments | CSP, 3PAO
3.4 | Agency Validated Comments | Agency
3.5 | Agency Approved SAP | Agency
4 | Develop and Finalize SAR / POA&M
4.1 | Conduct Security Assessment | 3PAO |  |  | *Start date should be within 6 months of In Process designation date
4.2 | Remediate Risks | CSP
4.3 | Finalize and deliver SAR | 3PAO
4.4 | Develop and deliver POA&M | CSP
4.5 | Hold SAR Debrief | CSP, 3PAO, Agency, PMO |  |  | Formal meeting with FedRAMP PMO, Agency, 3PAO, and CSP
4.6 | Review & Approve SAR | Agency
5 | Final Agency Review and ATO |  |  |  | End date should be expected date of ATO issuance from Agency
5.1 | Agency final review | Agency
5.2 | Agency submits CSO’s authorization package to the Agency AO for final approval and issuance of the ATO | Agency
5.3 | Agency issues ATO and provides copy to FedRAMP via info@fedramp.gov | Agency
6 | FedRAMP PMO Review and FedRAMP Authorized Decision
6.1 | The CSP and 3PAO upload all required security package material to OMB MAX | CSP, 3PAO
6.2 | The FedRAMP PMO reviews the package and releases an Agency Package Review Report | PMO |  |  | FedRAMP is committed to a package reiew within 10 days; CSP package is put in queue according to order received
6.3 | Conduct review meeting with agency, CSP, and 3PAO to discuss questions on outstanding items reflected in the Agency Package Review Report | CSP, 3PAO, Agency, PMO |  |  | Once complete package is uploaded to OMB Max PMO will work with CSP to set up a date for meeting
6.4 | Remediation of PMO findings and delivery of updates to PMO | CSP, 3PAO |  |  | This timeline will vary depending on FedRAMP findings
6.5 | PMO informs CSP that FedRAMP Authorization designation has been achieved | PMO
6.6 | Marketplace listing for CSO is updated to reflect FedRAMP Authorized and date of authorization | PMO |  |  | *End date should be within 1 year of In Process designation date